## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-SP-0013-D05 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2703 |  |  | Transmital Date: 29-MAY-2024
Document Title: SPECIFICATION FOR FLARE PACKAGE |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0303-ME-TR-2703 |  |  | Transmital Date: 29-MAY-2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0013-D06 |  |  | CRS Status: | CM
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در بخش 3.3 مدرکی با عنوان Basic of Design Control System & Instrumentn درج شده است که در لیست مدارک پروژه این مدرک (BK-GNRAL-PEDCO-110-IN-DB-0001) وجود ندارد و در این پروژه تولید نشده است. |  | 1403-2294-208684 | 1403/06/03 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته شد و مدرک Instrument & Control System Design Criteria با همین مضمون تولید شده است که جایگزین مدرک Basic of Design Control System & Instrumentn گردید.
2 | با توجه به اینکه در این مدرک به تمام داده های فرآیندی اشاره نمیشود لذا میبایست در بخش رفرنس به آخرین ویرایش مدارک بخش فرآیند که در فاز مهندسی تفضیلی نهایی گردیده اشاره شود و ملاک طراحی قرار گیرد. |  | 1403-2294-208684 | 1403/06/03 | نقطه نظر کارفرمای محترم مد نظر قرار گرقته شد
| FLARE NETWORK STUDY REPORT-REV-D07 Flare Radiation & Despersion Study Report-Rev-D05 DUTY SPECIFICATION FOR LP FLARE PACKAGE-Rev-D05 |  |  | 1403/06/03
3 | میبایست تعداد Blowerهای پکیج فلر دو عدد( بصورت Duty/ stand by) و هر کدام مجز به VFD باشد |  | 1403-2294-208684 | 1403/06/03 | با توجه به مکاتبات و شفاف سازی های صورت گرفته موارد مرتفع گردید
2 | میزان ظرفیت Smokeless فلر میبایست برای کل میزان گاز در نظر گرفته شود. |  | 1403-2294-208684 | 1403/06/03 | با توجه به مکاتبات و شفاف سازی های صورت گرفته موارد مرتفع گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 12.28.2024