## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PI-DW-0005-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1133 |  |  | Transmital Date: 02-July-2022
Document Title: U/G Piping Plan |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-01043-PI-TR-1133 |  |  | Transmital Date: 02-July-2022
[5 empty] | CRS No: PEDCO-BK-GCS-PEDCO-120-PI-DW-0005-D01 |  |  | CRS Status: | C3
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | عدم تداخل با ديگر ابنيه و تأسيسات زيرزميني و روزميني و رعايت حريم هاي مورد نظر با ديسيپلين هاي مربوطه كنترل و بررسي گردد. |  | BK-SUR-ENG-PIP-01-05004 | 2022-07-05 | احتراما نقطه نظر اعمال گردید.
2 | مدرك مطابق با آخرين كامنتهاي مربوط به بررسي مدل PDMS نهايي گردد وهمچنين مطابق با نقشه هاي سيويل مربوطه باشد. |  | BK-SUR-ENG-PIP-01-05004 | 2022-07-05 | احتراما نقطه نظر اعمال گردید.
3 | بقيه كامنتها بصورت مارك شده در مدرك پيوست مي باشد. |  | BK-SUR-ENG-PIP-01-05004 | 2022-07-05 | احتراما پاسخ موارد به پیوست ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: J.Mousazadeh | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 05.July.2022 |  |  |  |  | Date : 05.July.2022