## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-LI-0002-D04 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2435 |  |  | Transmital Date: 16-Oct-2023
Document Title: I/O List For Control System |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0207-IN-TR-2435 |  |  | Transmital Date: 16-Oct-2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-NISOC-120-IN-LI-0002_D05 |  |  | CRS Status: CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
| بعد از نهایی سازی مدارک سازندگان پکیجها، این مدرک نیز بروز رسانی گردد. |  | 02/2294/307650 | 1402/08/03 | ملاحظه شد.
* | بدیهی است که مسئولیت تطابق مدارک اصلاحی با نقطه نظرات کارفرما و همچنین صحت و کفایت محتوای کلیه مدارک ارسالی مطابق شرح خدمات و استانداردهای تصریح شده در اسناد مناقصه، استانداردهای IPS و دیگر مدارک پروژه بر عهده پیمانکار بوده و نقطه نظرات کارفرما رافع مسئولیت پیمانکار نمی باشد. |  | 02/2294/307650 | 1402/08/03 | ملاحظه شد.
مطابق آخرین P&ID و مدارک پروژه جهت خرید سیستم کنترل به روز رسانی گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: 30 Oct 2023 |  |  |  |  | Date: