## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-HV-DT-0002_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2631 |  |  | Transmital Date: 11-MAR-2024
Document Title: Data Sheets For Main HVAC Equipment of Extension of Existing Elect. Building |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0212-HV-TR-2631 |  |  | Transmital Date: 11-MAR-2024
[5 empty] | CRS No: NISOC-CRS- BK-GCS-PEDCO-120-HV-DT-0002_D01 |  |  | CRS Status: | C2
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | فرمت Data Sheet ارسالی قابل قبول نمی باشد.لازم است مشخصات دستگاه ها در مدرک و فرم مخصوص Data Sheet درج گردد. این مدرک باید شامل بخشهایی از قبل Introduction، Scope Of Work، Cods and standard، Refrence Document و HVAC Equipment Schedule باشد. |  | 03/2294/21121 | 1403/01/26 | فرمت مدرک اصلاح گردید.
2 | با توجه به بررسی ترنسمیتال 2630، مدرک فوق پس از نهایی سازی مدرک پیشنیاز (Calculation) جهت بررسی و اظهار نظر ارسال گردد. |  | 03/2294/21121 | 1403/01/26 | ویرایش D04 مدرک محاسبات مورد تایید قرارگرفته است لذا محتوای فنی بر اساس مفاد مدرک مزبور اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: 1403/01/26 |  |  |  |  | Date: