## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DT-0018 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2353 |  |  | Transmital Date: 11-Sep-2023
Document Title: Data Sheets For Rotameter |  |  |  |  | NISOC Tr. No.: BK-PEDCO-NISOC-0206-IN-TR-2353 |  |  | Transmital Date: 11-Sep-2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-DT-0018_D03 |  |  | CRS Status: | C2
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | برای تگ FG-2111 مقدار METER SCALE RANGE اصلاح گردد. |  | 02/2294/292522 | 1402/07/25 | مدرک اصلاح گردید.
2 | در مورد تگ FG-2272 واحد اندازه گیری جریان خط و فلومتر همسان گردد. |  | 02/2294/292522 | 1402/07/25 | مدرک اصلاح گردید.
3
4
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 18 sep 2023 |  |  |  |  | Date: