## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0013 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1895 |  |  | Transmital Date: 25-Feb- 2023
Document Title: PMR FOR OVERHEAD TRAVELLING CRANES |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-1895 |  |  | Transmital Date: 25-Feb- 2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0013_D01 |  |  | CRS Status: | CM-C2
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به عدم نهايي سازي مدارك پيش نياز از جمله sepc و Data sheet مربوطه ، مطابق نظر كارفرما ارسال مجدد اين مدرك منوط به نهايي شدن مدارك پيش نياز آن مي باشد، لذا مدرك در اين مقطع قابل بررسي نمي باشد.بديهي است پس از نهايي شدن مدارك پيش نياز اين مدرك مي بايست بصورت جايگزين ارسال گردد. |  | BK-SUR-ENG-MEC-01-07005 | 2023-02-25 | با توجه به نهایی شدن مدارک ذکر شده و اکثر مدارک پیوست خواهشمند است بررسی مدرک در دستور کار آن کارفرمای محترم قرار گیرد
2 | در بند 5.1.1، عبارت "QA Organization" به "QA/QC Organization Chart" تغيير يابد. |  | BK-SUR-ENG-MEC-01-05751 | 2022-09-24 | Noted
3 | در بند 6: 1-عبارت "Project ITP Procedure" به "Commodity Procurement and Manufacturing Inspection Instruction" تغيير يابد. 2-دستورالعمل انتخاب سطح بازرسي كالا و تجهيزات به شماره مدرك ICE-EID-MI-SP02-REV-01 اضافه گردد. |  | BK-SUR-ENG-MEC-01-05751 | 2022-09-24 | Noted
4 | در جدول بند 11.2: -در رديف 1، عبارت "See Attachment 2" حذف گردد. - عبارت "List of Documents will be Finalized in VPIS" در نوتها اضافه گردد. |  | BK-SUR-ENG-MEC-01-05751 | 2022-09-24 | Noted
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: M.Fakharian | Signature
| Date: 2/25/2023 |  |  |  |  | Date: 1/6/2025