## CRS-D06
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-SA-PI-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2810 |  |  | Transmital Date: 27-Oct-2024
Document Title: P&ID - Fire Water Network |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0308-SA-TR-2810 |  |  | Transmital Date: 27-Oct-2024
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-SA-PI-0001-D07 |  |  | CRS Status: C2-CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | BK-SUR-ENG-SAF-03-09677 | 1403/08/23 | تمامی کامنت های مربوطه در رویژن جدید اعمال گردید. برخی از کامنت ها که اعمال نشد به شرح زیر می باشد:
کامنت در صفحه دوم در مورد مشخص شدن شماره خط: خط مربوطه در جای دیگر مشخص شده و ادامه هدر می باشد. FWA-113-0025-AN04-12"-PT
کامنت بخش ابزار دقیق در صفحه دوم مربوط به گذاشتن PAL و نیز auto/manual switch in LCS: هر دوی این موارد در رویژن 4 مدرک بوده و بعد از کامنت کارفرما در رویزن بعد برداشته شده است. نظر کارفرما بر این بوده که فشار توسط بالا دست و PT 2301 و با دستور به MCC کنترل گردد
کامنت در صفحه سوم برای در نظر گرفتن شماره خط برای انشعابات بعد از بالای زمین رفتن خطوط مربوط به هایدرنت و مانیتور: این خطوط نیز در رویژن 4 مدرک بوده و بعد از کامنت کارفرما حذف گردیده. در ضمن خط آب زیر زمین بعد از بالا امدن بلافاصله به هایدرنت/مانیتور متصل می گردند.
کامنت در صفحه چهارم و صفحه دوم در مورد مشخص کردن تمامی دیتیل های باکس های مربوط به وندور: مشخصات اصلی باکسهای مربوط به وندور در PID آمده است. دیتیل تمامی آنها توسط خود وندور داده می شود. مشخصاتی مانند سایز شیرها و نوع اتصال به خط و یا سایز اتصال ادوات ابزار دقیق توسط وندور تهیه می شود و چیدمان اصلی آنها در PID مشخص شده.
کامنت در صفحه سوم در مورد تگ HR برای HOSE REEL : ادوات نشان داده شده، هایدرنت بوده و تگ آنها به درستی با FH نشان داده شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.MALEKI | Signature |  |  |  | Clarified By: | Signature
| Date: 10/11/2024 |  |  |  |  | Date: