## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-220-AR-DW-0011 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2830 |  |  | Transmital Date: 10-NOV-2024
Document Title: Architectural Detail Drawing For Extension of CONTROL Building |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0308-AR-TR-2830 |  |  | Transmital Date: 10-NOV-2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-220-AR-DW-0011_D05 |  |  | CRS Status: | AN
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بازگشت به جوابیه پیمانکار (بند یک ریپلای شیت) در خصوص ارتفاع اسلیوها از کف به میزان نیم متر، تراز ارتفاعی B.O.S برای اسلیو ارتباطی مورد اشاره 0.75+ می باشد، اصلاح گردد. |  | 1403-2294-412879 | 1403/10/15 | با هماهنگی بخش برق، ارتفاع اسلیوها اصلاح گردید.
Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
| CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date:
12
13
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
Legend
Signature