## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DT-0012 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2260 |  |  | Transmital Date: 23-Jul-2023
Document Title: Data Sheets For Diff. Pressure Flow Transmitter |  |  |  |  | NISOC Tr. No.: BK-PEDCO-NISOC-0205-IN-TR-2260 |  |  | Transmital Date: 23-Jul-2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-DT-0012_D04 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدرک مطابق با آخرین ویرایش مدرک P&ID اصلاح گردد. به عنوان نمونه سایز خط مربوط به FIT-2271 اصلاح گردد. |  | 02/2294/232373 | 1402/06/13 | مدرک مطابق نظر کارفرمای محترم اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 31 Jul 2023 |  |  |  |  | Date: