## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DT-0012 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2260 |  |  | Transmital Date: 23-Jul-2023
Document Title: Data Sheets For Diff. Pressure Flow Transmitter |  |  |  |  | NISOC Tr. No.: BK-PEDCO-NISOC-0205-IN-TR-2260 |  |  | Transmital Date: 23-Jul-2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-DT-0012_D04 |  |  | CRS Status: | C2
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-02-08202 | 2023-08-01 | ملاحظه گردید.
2 | با توجه به اينكه مدارك پيش نياز اين مدرك نهايي نشده است، در صورت هر گونه تغيير در اين مدرك نيز بايد منعكس گردد. نهايي شدن شدن اين مدرك منوط به نهايي شدن مدارك پيش نياز مي باشد. |  | BK-SUR-ENG-INS-02-08202 | 2023-08-01 | ملاحظه گردید.
3 | با توجه به اينكه اين مدرك و مدارك موجود در اين ترانسميتال داراي كامنت بوده، ترانسميتال به كارفرما ارسال نشده است، مدارك مجددا با همين رويژن و همين شماره ترانسميتال در اسرع وقت جايگزين گردد. |  | BK-SUR-ENG-INS-02-08202 | 2023-08-01 | مدرک قبل تر با ترنسمیتال T-2411 مجددا ارسال گردیده شده است و این نسخه از مدرک مطابق آخرین نظرات کارفرما(NISOC/PEDCO) اصلاح و بروز رسانی شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 31 Jul 2023 |  |  |  |  | Date: