## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-IN-SP-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0234 |  |  | Transmital Date: 14-Nov-2021
Document Title: SPECIFICATION FOR INSTRUMENTATION |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0008-IN-TR-0234 |  |  | Transmital Date: 14-Nov-2021
[5 empty] | CRS No: NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در خصوص بند 9 از Reply Sheet ارسالی توضیحات پیمانکار در صورتی صحیح است که جمله ای مرکب یا مختلط داشته باشیم. در دو پاراگراف و یا خط جداگانه نمی توان عنصری را به قرینه حذف نمود. لازم است موارد اینچنینی در نسخه نهایی ارسالی تصحیح شوند. |  | 00/2294/283469 | 1400/08/30 | مطابق نظر درست کارفرما این جمله تصحیح گردید و در تمامی متن مواردی اینچنینی تصحیح شد.
2 | در این مقطع زمانی در خصوص این مدرک نظر خاصی مطرح نمی باشد. |  | 00/2294/283469 | 1400/08/30 | -
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: