## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-MR-0008 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2335 |  |  | Transmital Date: 03-SEP-2023
Document Title: PMR For Corrosion Probe/Coupon |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0206-TR-IN-2335 |  |  | Transmital Date: 03-SEP-2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-MR-0008-D02 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | عبارات Subvendor , Supplier (درج‌شده در متن) در بخش Definition of Terms درج گردند. |  | 02/2294/269272 | 1402/07/10 | با توجه به توافقات به نظر کارفرمای محترم مدرک اصلاح گردید.
2 | هنگام ارسال اين مدرک برای تایید نهایی می‌بایست شماره ویرایش نهایی مدارک مرجع درج‌ گردد. |  | 02/2294/269272 | 1402/07/10 | مدرک مطابق آخرین نسخه از مدارک پیش نیاز تهیه گردید.
3 | شماره Tag Number برای آیتم شماره ۷ جدول تجهیزات CC-2161 مطابق مدرک P&ID نمی باشد. |  | 02/2294/269272 | 1402/07/10 | با توجه به توافقات صورت گرفته و دیگر مدارک PMR پروژه، تگ و تعداد تجهیزات از این مدرک حذف گردید و برای مشاهده این موارد به دیتاشیت مربوطه رجوع گردد.
4 | مسئولیت راه‌اندازی تجهیزات(در مدارک دارای موضوعیت) افزوده گردد. |  | 02/2294/269272 | 1402/07/10 | در مواقع مورد نیاز، نظر کارفرمای محترم لحاظ خواهد شد.
5 | در بند ۶ مدرک INSPECTION AND TESTS لازم است مدرک ITP به تایید کارفرما برسد. بنابراین در عبارت VENDOR or CLIENT کلمه OR به AND اصلاح گردد. |  | 02/2294/269272 | 1402/07/10 | با توجه به توافقات به نظر کارفرمای محترم مدرک اصلاح گردید.
6 | با توجه به لزوم نهایی سازی مدارک پیش نیاز از جمله دیتاشیت و HOOK UP لازم است این مدرک پس از تایید نهایی مدارک پیش نیاز دوباره برای بررسی ارسال گردد. |  | 02/2294/269272 | 1402/07/10 | مدرک مطابق آخرین نسخه از مدارک پیش نیاز تهیه گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: