## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-MR-0016 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2673 |  |  | Transmital Date: 1-May-2024
Document Title: PMR FOR LEVEL SWITCH |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0302-IN-TR-2673 |  |  | Transmital Date: 1-May-2024
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-MR-0016_D03 |  |  | CRS Status: | C1
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | محتواي مدرك با نام مدرك ارسالي همخواني ندارد. |  | BK-SUR-ENG-INS-01-05623 | 2022-09-10 | اصلاح گردید. |  |  | بسته شد.
D01
1 | در این مقطع نقطه نظر خاصی مطرح نمی باشد. بدیهی است که در صورت تغییر در هر کدام از مدارک مرتبط در این مدرک نیز در نظر گرفته شود. |  | BK-SUR-ENG-INS-02-08482 | 2023-09-18 | ملاحظه گردید
2 | به دلیل اینکه مدرک PMR for Rotameter که در این ترانسمیتال قرار دارد عودت داده شده است؛ مجددا این مدرک با همین شماره مجددا ارایه گردد. |  | BK-SUR-ENG-INS-02-08482 | 2023-09-18 | ملاحظه گردید
D02
1 | در این مقطع نقطه نظر خاصی مطرح نمی باشد. |  | BK-SUR-ENG-INS-03-09344 | 2024-05-29 | ملاحظه گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: 15 May 2024 |  |  |  |  | Date: