## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DT-0010 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-NISOC-T-2836 |  |  | Transmital Date: 16-Nov-2024
Document Title: Data Sheets For ON/OFF & Shutdown Valves |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0308-IN-TR-2836 |  |  | Transmital Date: 16-Nov-2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-DT-0010_D04 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اینکه این مدرک در ویرایش پیشین بصورت AFC تایید شده است و ملاک عمل سازندگان در TBE می باشد. پیمانکار اجازه تغییر موارد فنی را در این مرحله ندارد و تنها مجاز به حذف شیرهای مربوط به مسئله Purging می باشد و در مورد سایر شیرها بدون تغییر مجددا برای تایید کارفرما ارسال گردد و ملاک عمل قرارداد و ساخت قرار گیرد. در صورت تکرار این روال (تغییر مدرک AFC تایید شده از جانب پیمانکار بدون هماهنگی با کارفرما و توجیه منطقی) در سایر مدارک مطابق پیمان عمل خواهد شد. |  | 3/2294/368023 | 1403/09/13 | مدرک مطابق آخرین تغییرات مدارک مرجع از جمله P&ID های مربوطه ، SIl STUDY REPORTو نیز SPECIFICATION FOR ON /OFF, SHUTDOWN VALVES (ESDMOV)صلاح و بروز رسانی شده است. لازم به ذکر است تغییرات در جهت مسئولیت پیمانکار برای همسان سازی مدارک ( که درنامه تایید مدرک ذکر شده است ) انجام شدو کلیه تغییرات برای ملاحظه کارفرمای محترم مارک شده بود. خواهشمند است در جهت یکسان سازی مدارک تغییرات پذیرفته شود.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri P.Maleki S.Akbari | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: 1 Dec 2024 |  |  |  |  | Date: