## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-LD-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2636 |  |  | Transmital Date: 12 Mar 2024
Document Title: ESD Logic Diagram |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0212-IN-TR-2636 |  |  | Transmital Date: 12 Mar 2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-NISOC-120-IN-LD-0002_D02 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
- | با توجه به تصمیمات اتخاذ شده در جلسه مربوط به SIL & HAZOP STUDY کمپرسور گازی در تاریخ 22 و 23 اسفند ماه 1402 ، لازم است پس از اعمال تغییرات لازم این مدرک دوباره جهت بررسی و تایید کارفرما ارسال گردد. |  | 1403-2294-20873 | 1403/01/25 | به روز رسانی شد.
* | بدیهی است مه مسئولیت تطابق مدارک اصلاحی با نقطه نظرات کارفرما و همچنین صحت و کفایت محتوای کلیه مدارک ارسالی مطابق شرح خدمات و استانداردهای تصریح شده در اسناد مناقصه، استانداردهای IPS و دیگر مدارک پروژه بر عهده پیمانکار بوده و نقطه نظرات کارفرما رافع مسئولیت پیمانکار نمی باشد. |  | 1403-2294-20873 | 1403/01/25 | ملاحظه شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: 26 Mar 2024 |  |  |  |  | Date: