## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DC-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2904 |  |  | Transmital Date: 7-JAN-2025
Document Title: Instrument & Control System Design Criteria |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0310-IN-TR-2904 |  |  | Transmital Date: 7-JAN-2025
[5 empty] | CRS No: NISOC-CRS-BK-GCS-NISOC-120-IN-DC-0002_D03 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | لازم است NOTE مربوط به بخش 5.2.3 اصلاح و رفع ابهام گردد، بدین گونه که برای سیستم F&G یک سیتم به صورت مشترک برای EWS و OWS و برای سیستم ESD (جدا از سیستم F&G) یک سیستم به صورت مشترک برای EWS و OWS در نظر گرفته شود. |  | 03-2294-439270 | 1403/11/03 | اصلاح شد.
2 | لازم است در قالب یک NOTE عنوان شود که برای سیستم های بند 1 یوزرهایی با سطح دسترسی متفاوت برای اپراتوری و مهندسی تعریف گردد. |  | 03-2294-439270 | 1403/11/03 | در بخش 5.2.3 سطوح دسترسی View Only Level, Operator Level, Supervisor Level و Engineering Level عنوان شده است. لازم به ذکر است که این قابلیت ها بصورت نرم افزاری قابل تنظیم هستند.
* | بدیهی است که مسئولیت تطابق مدارک اصلاحی با نقطه نظرات کارفرما و همچنین صحت و کفایت محتوای کلیه مدارک ارسالی مطابق شرح خدمات و استانداردهای تصریح شده در اسناد مناقصه، استاندارد های IPS و دیگر مدارک پروژه بر عهده پیمانکار بوده و نقطه نظرات کارفرما رافع مسئولیت پیمانکار نمی باشد. |  | 03-2294-439270 | 1403/11/03 | ملاحظه شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 19 Aug 2023 |  |  |  |  | Date: