## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DC-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2904 |  |  | Transmital Date: 7-JAN-2025
Document Title: Instrument & Control System Design Criteria |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0310-IN-TR-2904 |  |  | Transmital Date: 7-JAN-2025
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-DC-0002_D03 |  |  | CRS Status: | C4
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | تعداد workstation ها مجددا بررسي و بر اساس نيازمندي هاي پروژه بروز گردند. |  | BK-SUR-ENG-INS-02-08299 | 2023-08-19 | اصلاح شد
2 | جدول كانكشن ها مجددا بررسي گردد. |  | BK-SUR-ENG-INS-02-08299 | 2023-08-19 | اصلاح شد
3 | در خصوص بخش مربوط به UCPها، به نوع UCP اشاره گردد. (دراين مدرك يا spec مربوطه) |  | BK-SUR-ENG-INS-02-08299 | 2023-08-19 | اصلاح شد
4 | Zone 1 اصلاح گردد. |  | BK-SUR-ENG-INS-02-08299 | 2023-08-19 | اصلاح شد
5 | رفرنس مدارك مرجع اصلاح گردد. |  | BK-SUR-ENG-INS-02-08299 | 2023-08-19 | اصلاح شد
6 | در سيستم F&G به FACP اشاره گردد. |  | BK-SUR-ENG-INS-02-08299 | 2023-08-19 | اصلاح شد
7 | تناقضات بين مدارك برطرف گردد. |  | BK-SUR-ENG-INS-02-08299 | 2023-08-19 | اصلاح شد
8 | با توجه به كامنت هاي ذكر شده در بالا و مذاكره تلفني مدرك و ترانسميتال مجددا با همين شماره ارائه گردد |  | BK-SUR-ENG-INS-02-08299 | 2023-08-19 | مدرک جایگزین شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 19 Aug 2023 |  |  |  |  | Date: