## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DG-0004 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2654 |  |  | Transmital Date: 9 Apr 2024
Document Title: ESD System Loop Diagram |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0301-IN-TR-2654 |  |  | Transmital Date: 9 Apr 2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-NISOC-120-IN-DG-0004_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به جلسه HAZOP مورخ 1402/12/22 و تغییرات اعمالی در فرایند تخلیه کمپرسور و تاثیرات آن روی این مدرک، لازم است این مدرک پس از اعمال تغییرات مجددا برای بررسی و تائید کارفرما ارسال گردد. |  | 03-2291-44362 | 1403/02/08 | مدرک ESD LOOP DIAGRAM عطف به آخرین رویژن مدرک P&ID و پیرو آن ESD I/O List به روز رسانی شد. بدیهی است تاثیرات جلسات HAZOP و SIL ، در مدارک P&ID و I/O List لحاظ شده است.
* | بدیهی است مسئولیت تطابق مدارک اصلاحی با نقطه نظرات کارفرما و همچنین صحت و کفایت محتوای کلیه مدارک اصلاحی مطابق شرح خدمات و استاندارد های تصریح شده در اسناد مناقصه، استانداردهای IPS و دیگر مدارک پیش نیاز بر عهده پیمانکار بوده و نقطه نظرات کارفرما رافع مسئولیت پیمانکار نمی باشد. |  | 03-2291-44362 | 1403/02/08 | ملاحظه شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: 1403/02/08 |  |  |  |  | Date: