## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GNRAL-PEDCO-000-IN-SP-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0495 |  |  | Transmital Date:1/23/2022
Document Title:Specification For Control System |  |  |  |  | NISOC Tr. No.: BK-PEDCO-NISOC-0011-IN-TR-0495 |  |  | Transmital Date:1/23/2022
[5 empty] | CRS No:NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0002-D03 |  |  | CRS Status: | AN
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در قسمت Scope هرگونه تغییرات یا اختلاف در مشخصات در هر مقطع از پروژه باید به تایید Client برسد. |  | 1400-2294-441071 | 1400/12/17 | تغییرات در این نسخه و نسخه های قبلی برای بررسی و تایید کارفرمای محترم همراه با Revision Mark و به رنگ خاکستری مشخص گردیده است. این مدرک مطابق آخرین توافقات در جلسات HAZOP و نظرات کارفرما بر روی سایر مدارک به روز رسانی شد.
2 | با توجه به ماده 13 شرایط عمومی پیمان و نظر به وظایف ومسئولیت های کامل مالی/قراردادی پیمانکار، در این مقطع با انجام تغییرات فوق الذکرجهت مدرک اشاره شده، نظر دیگری مطرح نمییاشد. پیشبرد گام بعدی مهندسی مدارک و انتشار AFC بلامانع است |  | 1400-2294-441071 | 1400/12/17 | مطابق نظر کارفرمای محترم مدرک پس از یکسان سازی با سایر مدارک مهندسی ، به صورت نسخه AFD ارسال میگردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 15 Jan 2022 |  |  |  |  | Date: