## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-EL-DT-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-TR-2798 |  |  | Transmital Date: 14/Oct/2024
Document Title: Data Sheets For UPS |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0307-EL-TR-2798 |  |  | Transmital Date: 14/Oct/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0001-D05 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | آیتم 7 : Rated power میبایست به Input rated Power اصلاح گردد توان اشاره شده مربوط به توان ورودی جذب شده مورد نیاز UPS از شبکه برق باشد. |  | 03/2294/381338 | 1403-09-21 | اصلاح گردید.
2 | ییرو بند 13 صورت‌جلسه مورخ 1403/05/14 و نامه شماره 1403/2391/18640 مورخ 1403/05/17 و پذیرش تبعات فرآیند خرید با اطلاعات پیش‌فرض و بر اساس کاتالوگ سازندگان در پروژه مشابه (ناشی از عدم وجود اطلاعات سازندگان تابلوها) توسط پیمانکار، لازم است در صورت هر گونه تغییر در لیست بارهای سیستم ابزار دقیق (پس از نهایی شدن مدارک طراحی سازنده)، ضمن اخذ تأیید از بخش ابزار دقیق این امور، در صورت نیاز نسبت به اصلاح محاسبات و پارامترهای مرتبط در داده‌برگ اقدام گرد. |  | 03/2294/381338 | 1403-09-21 | لازم به ذکر است این نسخه از مدرک بر اساس آخرین اطلاعات دریافتی از سازندگان مورد بازنگری قرار گرفته است.
3 | با عنایت به تعهدات پیمانکار و در صورت رعایت ملاحظات فوق‌الذکر، مدرک حداقل‌های لازم جهت اخذ پیشنهادات فنی سازندگان را دارا می‌باشد |  | 03/2294/381338 | 1403-09-21 | مورد تایید است.
3 | بدیهی است که مسئولیت تطابق مدارک اصلاحی با نقطه‌نظرات کارفرما و همچنین صحت و کفایت محتوای کلیه مدارک ارسالی مطابق شرح خدمات و استانداردهای تصریح‌شده در اسناد مناقصه، استانداردهای IPS بر عهده پیمانکار بوده و نقطه‌نظرات کارفرما رافع مسئولیت پیمانکار نمی‌باشد. |  | 03/2294/381338 | 1403-09-21 | مورد تایید است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M.Karimi | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: 10-Feb-24 |  |  |  |  | Date: