## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-EL-SL-0005 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2129 |  |  | Transmital Date: 21-May-2023
Document Title: UPS Single Line Diagram |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0202-EL-TR-2129 |  |  | Transmital Date: 21-May-2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0005_D02 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق مدرک مرجع پیکربندی سیستمن UPS ارسالی ،تابلوی توزیع 110VAC یکی از اجزای سیستم UPS میباشد،لذا طراحی و ساخت آن یصورت جداگانه مورد تایید نیست. |  | 02/2294/95482 | 1402/03/11 | سیستم UPS به همراه تابلوی توزیع آن بصورت یکپارچه خریداری خواهد شد.
1 | کاربرد دستگاه کانورتر 24VDC اشاره شده در Note 15 در این پروژه مشخص نیست. |  | 02/2294/95482 | 1402/03/11 | Note 15 در خصوص این مورد حذف گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 17-Aug-22 |  |  |  |  | Date: