## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DT-0019 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-TR-2411 |  |  | Transmital Date: 8 Oct 2023
Document Title: Data Sheets For Diff. Pressure Type Level Transmitter |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0207-IN-TR-2411 |  |  | Transmital Date: 8 Oct 2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-DT-0019_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در لیست ادوات بند 4 مقدار SIL a اصلاح گردد. |  | 02/2294/293034 | 1402/07/25 | مطابق مدرک SIL REPORT FOR COMPRESSOR STATION برای این تجهیز SIL a در نظر گرفته شده است که مطابق خواست کارفرمای محترم بصورت SIL RATED اصلاح گردید.
2 | در بند 17 جدول دیتاشیت (OUTPUT SIGNAL)و NOTE 2 لیست، عبارت SMART قبل از HART اضافه گردد. این مورد در پاسخ های پیشین نیز تذکر داده شده است. |  | 02/2294/293034 | 1402/07/25 | مدرک مطابق خواست کارفرمای محترم اصلاح گردید.
3 | خاطر نشان می سازد در تهیه مدارک، پاسخ های پیشین را با دقت در نظر گرفته و در رفع آن ها اقدام گردد و از ارائه پاسخ های مبهم و دو پهلو خودداری شود. |  | 02/2294/293034 | 1402/07/25 | نظرات کارفرمای محترم در مدرک اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 22 Oct 2023 |  |  |  |  | Date: