## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-DT-0009 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2209 |  |  | Transmital Date: 18 Jun 2023
Document Title: Data Sheets For Corrosion Coupon/ Probe |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0203-IN-TR-2209 |  |  | Transmital Date: 18 Jun 2023
[5 empty] | CRS No: NISOC-CRS-BK-PPL-PEDCO-320-IN-DT-0009_D02 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در خصوص حذف کوپن خوردگی و پراب خوردگی CC-3201/CP-3201 شفاف سازی گردد. |  | 02/2294/157834 | 1402/04/24 | این مدرک بر اساس مدرکP&ID مرجع P&ID - Gas Pipeline (to Siahmakan G.I. Station) تهیه شده است که در این مدرک تنها کوپنCC-3201 موجود می باشد و بقیه تجهیزات خوردگی حذف شده اند.( علت حذف وجود تجهیزات موازی در سمت ایستگاه تقویت فشار میباشد)
2 | پیرو نامه 85248 مورخ 1401/03/10 در صورت استفاده از پراب خوردگی در سمت دریافت کننده توپک لازم است برای آن واحد نیز دستگاه اندازه گیر خوردگی قابل حمل در نظر گرفته شود. |  | 02/2294/157834 | 1402/04/24 | در سمت گیرنده توپک ( سایت سیاه مکان) پراب خوردگی وجود ندارد. در صفحه 4 از این مدرک ، Note 2، به تامین یک دستگاه اندازه گیر خوردگی قابل حمل توسط سازنده در سمت Launcher اشاره شده است .
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 2 Jul 2023 |  |  |  |  | Date: