## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-CV-CN-0003 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-1930 |  |  | Transmital Date:03/04/2023
Document Title:Calculation Note For Oily Contaminated Water Drainage Channels |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0112-CV-TR-1930 |  |  | Transmital Date:03/04/2023
[5 empty] | CRS No:NISOC-CRS-BK-GCS-PEDCO-120-CV-CN-0003_D02 |  |  | CRS Status: | AP
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظر به اینکه مطابق ماده 13 شرایط عمومی پیمان ، تصویب اسناد و مدارک مهندسی و طراحی از سوی کارفرما از هیچ یک از مسئولیتها و تعهدات قراردادی پیمانکار نمی کاهد، صدور مدارک AFC بلامانع است. |  | 1402-2294-3615 | 1402/01/07 | مدرک بر اساس اطلاعات فرآیندی، شرایط واقعی ایستگاه موجود و مستندات قراردادی بروز رسانی و مجددا ارائه میگردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: