## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PI-MR-0004 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2702 |  |  | Transmital Date: 05/26/2024
Document Title: PMR For Manual Valves |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0303-TR-PI-2702 |  |  | Transmital Date: 05/26/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PI-MR-0004_D02 |  |  | CRS Status: | C2
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | همانگونه که در نامه های شماره 01/2294/236199 و 02/2294/263626 بیان گردید، ساختار کلی مدارک مورد تایید بوده ولیکن ارسال نسخه بعدی مدارک فوق منوط به نهایی سازی کلیه ی مدارک مرتبط مهندسی و درج نسخ تایید شده(AFC) خواهد بود. لذا صدور نسخه جدید مدرک در حالی که مدارک پیشنیاز به طور کامل نهایی نشده است توجیه پذیر نبوده و تنها سبب مکاتبات مضاعف خواهد بود.در ضمن مزید تاکید اعلام میگردد از انجا که مسئولیت طراحی تفصیلی پروژه جزو تعهدات پیمانکار پروژه بوده و همچنین با استناد به وضعیت مدارک ارسالی (IFI)، مسئولیت کامل عدم تطابق متریال مندرج در این مدرک (مشخصات فنی و یا تعداد) در مرحله ی سفارش گذاری و خرید برعهده آن پیمانکار بوده و از این رو پیشبرد گام بعدی امکانپذیر است. |  | 03/2294/156251 | 1403/04/27 | مدارک پیش نیاز نهایی سازی شده و ارسال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: