## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-EL-DG-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2825 |  |  | Transmital Date: 09/Nov/2024
Document Title: Interconnection Wiring Diagrams For Cathodic Protection Systems for Siahmakan Gas Injection |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0308-EL-TR-2825 |  |  | Transmital Date: 09/Nov/2024
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-EL-DG-0003_D00 |  |  | CRS Status: | C3
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | There is conflict between this document and "Plan & Profile Drawings For Gas Pipeline (to Siahmakan)" document, from point of potential test box view. It shall be rechecked and modified. |  | BK-SUR-ENG-ELE-03-09717 | 2024-11-23 | Done
2 | Number of anode shall be rechecked and modified based on latest revision of cathodic protection calculation document. |  | BK-SUR-ENG-ELE-03-09717 | 2024-11-23 | Qty of anodes will be presented in the relevant documents. Such as CP design and MTO and this comment will be covered.
3 | The installation location of each T/R station shall be mentioned on page 2. |  | BK-SUR-ENG-ELE-03-09717 | 2024-11-23 | The locations of TRs will be finalized and checked at site in the latest site visit in 18 feb 2025, So this comments will be prepared in the related layout of CP underground layout and covered. |  |  | `
4 | Incoming/Outgoing type and size of cables for all boxes shall be added on pages 2 and 3. |  | BK-SUR-ENG-ELE-03-09717 | 2024-11-23 | Done
5 | Incoming cable size and type shall be added to on page 2 for transformer. Meanwhile AC box shall be shown too. |  | BK-SUR-ENG-ELE-03-09717 | 2024-11-23 | Done
6 | Description of TBC box on page 3 shall be added and number of it shall be rechecked and modified based on "Plan & Profile Drawings For Gas Pipeline (to Siahmakan)" document. |  | BK-SUR-ENG-ELE-03-09717 | 2024-11-23 | Done
7 | Type of anode shall be added on page 2. |  | BK-SUR-ENG-ELE-03-09717 | 2024-11-23 | Qty of anodes will be presented in the relevant documents. Such as CP design and MTO and this comment will be covered.
8 | "SP" description shall be added in legend. |  | BK-SUR-ENG-ELE-03-09717 | 2024-11-23 | Done
9 | This document shall be rechecked and modified after finalizing prerequisite documents such as cathodic calculation and layout. |  | BK-SUR-ENG-ELE-03-09717 | 2024-11-23 | Done
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozaffari | Signature |  |  |  | Clarified By: | Signature
| Date: 23/11/2024 |  |  |  |  | Date: