## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-EL-MR-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2826 |  |  | Transmital Date: 10/Nov/2024
Document Title: PMR For Cathodic Protection System |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0308-EL-TR-2826 |  |  | Transmital Date: 10/Nov/2024
[5 empty] | CRS No: NISOC-CRS-BK-PPL-PEDCO-320-EL-MR-0003_D00 |  |  | CRS Status: | RJ
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | و همچنین مدارک مرتبط در قسمت 1 ATTACHMENTصرفا به CATHODIC PROTECTION SYSTEM FOR SIAHMAKAN GAS INJECTION شده در حالیکه بخشی از تجهیزات در واحد تقویت فشار گازبینک و مسیر خط انتقال گاز نصب خواهند گردید لذا اصلاح گردد |  | 03/2294/402646 | 1403/10/09 | اصلاح شد.
2 | بدلیل عدم نهایی سازی مدارک پیش نیاز ) اغلب مدارک حفاظت کاتدی با ویرایش صفر مقتضی است از ارسال زودهنگام مدارک خودداری گردد لذا پس از نهایی سازی مدارک پیش نیاز نسبت به صدور مدرک اقدام گردد براساس توضیحات فوق الذکر مدرک مرجوع میگردد |  | 03/2294/402646 | 1403/10/09 | مدارک پیش نیاز به همراه بررسی بسته خرید با ویرایش اصلاحی و نهایی طی بازدید میدانی جهت بررسی مجدد ارسال میگردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozaffari | Signature |  |  |  | Clarified By: | Signature
| Date: 23/11/2024 |  |  |  |  | Date: