## CRS-D06
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-SA-PI-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2908 |  |  | Transmital Date: 07/JAN/2025
Document Title: P&ID - Fire Water Network |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0310-SA-TR-2908 |  |  | Transmital Date: 07/JAN/2025
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-120-SA-PI-0001_D07 |  |  | CRS Status: C3
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | سايز اعلام شده براي فلنج هاي ورودي و خروجي پمپ هاي main , diesel با ديتا شيت وندور تطابق ندارد |  | BK-SUR-ENG-SAF-03-09939 | 2025-01-08 | سایز reducer های ورودی و خروجی اصلاح گردید.
2 | نظرات فایل پیوست که شامل نظرات بخش پایپینگ و برق می باشد اعمال گردد. شایان ذکر است که مطابق شرایط عمومی پیمان فی ما بین و با توجه به مسئولیتهای مالی-قراردادی پیمانکار، مسئولیت بروز هرگونه اشتباه و تناقض، کمبود اسناد و مدارک فنی و اطلاعات تهیه شده از سوی پیمانکار اعم از اینکه از سوی کارفرما تایید شده و یا نشده باشد بر عهده پیمانکار است. |  | BK-SUR-ENG-SAF-03-09939 | 2025-01-08 | تمامی نظرات مربوطه اعمال گردید. در رابطه با وارد کردن اطلاعات مربوط به پکیج وندور، این موارد به صورت کامل در مدارک Az Built و مدارک وندور خواهد آمد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.MALEKI | Signature |  |  |  | Clarified By: | Signature
| Date: 08/01/2025 |  |  |  |  | Date: