## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-TE-PY-0005 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1848 |  |  | Transmital Date: Feb-07-2023
Document Title: Telecom Equipment Layout For Area |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0111-TE-TR-1848 |  |  | Transmital Date: Feb-07-2023
[5 empty] | CRS No: CRS-BK-GCS-PEDCO-120-TE-PY-0005_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظر خاصی مطرح نیست. در صورت جابجایی اتاق کنترل ،محل MDF میبایست در محل جدید اتاق کنترل نمایش داده شود. |  | 01/2294/454429 | 2023-02-19 | در نسخه نهایی مدرک ، شیت سوم اضافه و مسیر کابلهای مخابرات(مشترک با ابزار دقیق نمایش گردیده است) در نظر گرفته خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: