## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-TE-PY-0007 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2633 |  |  | Transmital Date: Mar-11th-2024
Document Title: Telecomm. Equipment Layout For Extension of Existing Control Building |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0212-TE-TR-2633 |  |  | Transmital Date: Mar-11th-2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-TE-PY-0007_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 03-2294-326778 | 1403-08-19 | به استحضار می رساند که برای هر ساختمان و هر فضا مدرک مجزایی تعریف شده است . مدارک ساختمان Electrical Buiding , CCB قبلا ارسال شده است ساختمان CCTV نیز بعد از نهایی شدن معماری ارسال میگردد . لذا بررسی مدرک لطفا به صورت مجزا طبق رویه پروژه انجام و نتیجه به این پیمانکار ارسال گردد شماره گذاری تابلو اتاق کنترل جدید و قدیم بر اساس رفرنس نقشه معماری میباشد و نقشه تایید شده میباشد revolving light مربوط به محیط بیرون و با نویز میباشد و داخل ساختمان کارایی ندارد . لطفا بیشتر شفاف گردد انقشه هاشور زده ستختمان موجود و اتاقهای موجود بوده که در آن قطعا سوکت تلفن موجود است . ما بقی نظرات کارفرمای محترم اعمال گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: AP.Golrang | Signature |  |  |  | Clarified By: | Signature
| Date: Sep-21th-2022 |  |  |  |  | Date: