## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ST-DW-0081 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-2946 |  |  | Transmital Date:2/15/2025
Document Title: Foundation Drawing For Extension of Existing Control Building |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0311-ST-TR-2946 |  |  | Transmital Date:2/15/2025
[5 empty] | CRS No:PEDCOC-CRS-BK-GCS-PEDCO-120-ST-DW-0081_D01 |  |  | CRS Status: | C1
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | کامنت های دریافت شده روی فایل |  | BK-SUR-ENG-STR-03-10060 | 2025-02-17 | کلیه کامنت ها در فایل پیوست پاسخ داده شده است
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: