## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DT-0016 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2833 |  |  | Transmital Date: 13 Nov 2024
Document Title: Data Sheets For F&G Detectors & Equipment |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0308-IN-TR-2833 |  |  | Transmital Date: 13 Nov 2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-DT-0016_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اينكه ویرایش پیشین این مدرک از جانب کارفرما تایید شده بود و ملاک عمل برای TBE قرار گرفته است ، پیمانکار مجاز به تغییرات موارد فنی نمی باشد. بنابراین لازم است سطح SIL را مانند ویرایش پیشین در نظر گرفته شود و برای TBE آخرین ویرایش مدرک مدنظر قرار گیرد. |  | 03/2294/392584 | 1403/10/01 | سطح SIL در این مدرک مطابق مدارک پروژه از جمله SIL Report For Compressor Station اصلاح گردیده شده است. در مدرک ذکر شده SIL 3 وجود ندارد و تنها SIL 2,SIL1 برای برخی تجهیزات در نظر گرفته شده است که در این مدرک نیزعبارت SIL3 اصلاح و بصورت SIL RATED ذکر گردید.
2 | با توجه به نظرات روی مدرک F&G LOCATION LAYOUT FOR BUILDINGS لازم است این مدرک بروز رسانی گردد. |  | 03/2294/392584 | 1403/10/01 | مدرک مطابق نقطه نظرات کارفرمای محترم بر روی مدرک F&G LOCATION LAYOUT FOR BUILDINGS بروز رسانی گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: s.akbari | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: 30 Nov 2024 |  |  |  |  | Date: