## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-IN-SP-0012 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0686 |  |  | Transmital Date: 6 Mar 2022
Document Title: Specification For Fire & Gas System |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0012-IN-TR-0686 |  |  | Transmital Date: 6 Mar 2022
[5 empty] | CRS No: NISOC-CRS-BK-GNRAL-NISOC-000-IN-SP-0012_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در این برهه و با توجه به مفاد ماده 13 شرایط عمومی پیمان، نظر خاصی مطرح نمی باشد. طبق رویه هماهنگی، پیمانکار نسبت به ارسال نسخ سخت برای این امور اقدام نماید. |  | 1400-2294-449047 | 1400/12/23 | مطابق آخرین Block Diagram Configuration For Control/ESD/F&G System به روز رسانی شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 16 Mar 2022 |  |  |  |  | Date: