## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-EL-MR-0014 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2520 |  |  | Transmital Date: 26-Dec-2023
Document Title: PMR For Power & Control Cables |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0210-EL-TR-2520 |  |  | Transmital Date: 26-Dec-2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-EL-MR-0014_D00 |  |  | CRS Status: | C1
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | No Comment. Note: This document shall be revised after finalzing prerequsite documents such as cable list and Cable MTO. For more information refere to the comments of releted documents. Consideration shall be given that the purchasing proccess shall be done after finalizing above mentioned documents. |  | BK-SUR-ENG-ELE-02-08932 | 2024-01-09 | مدارک پیشنیاز مانند CABLE CUTTING LISTوCABLE LIST و MTO بر اساس آخرین نقطه نظرات کارفرما و همچنین آخرین اطلاعات پروژه بروز گردیده و جهت جلوگیری از اتلاف وقت مدرک خرید با پیوست های بروز شده ارسال میگردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 09-Jan-2024 |  |  |  |  | Date: