## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-PY-0004 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2334 |  |  | Transmital Date: 3 sep 2023
Document Title: Instrument/F&G Cable Trench/Route Layout Drawing |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0206-IN-TR-2334 |  |  | Transmital Date: 3 sep 2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-PY-0004_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در مورد مدرک فوق نظر خاصی مطرح نمیباشد |  | 02/2294/285658 | 1402/07/22 | با توجه به آخرین پلات پروژه، مدارک سازندگان پکیج ها و مدرک cable list این مدرک به روز رسانی شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 20 sep 2023 |  |  |  |  | Date: