## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-MR-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2863 |  |  | Transmital Date: 12/11/2024
Document Title: PMR For F&G System |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0309-IN-TR-2863 |  |  | Transmital Date: 12/11/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-NISOC-120-IN-MR-0003_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | عبارت if any و other fee از مدارک حذف گردد. |  | 03-2294-416423 | 1403/10/17 | ملاحظه شد. در مدرک MR سیستم F&G این عبارات وجود نداشتند.
| بدیهی است که مسئوایت تطابق مدارک اصلاحی با نقطه نظرات کارفرما و همچنین صحت و کفایت محتوای کلیه مدارک ارسالی مطابق شرح خدمات و استانداردهای تصریح شده در اسناد مناقصه، استانداردهای IPS و دیگر مدارک پروژه بر عهده پیمانکار بوده و نقطه نظرات کارفرما رافع مسئولیت پیمانکار نمی باشد. |  | 03-2294-416423 | 1403/10/17 | ملاحظه شد.
این مدرک بر اساس آخرین تغییرات مدارک پایه از قبیل Control/ESD/F&G System Block Diagram Configuration و … به روز رسانی شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: