## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-EL-LI-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2979 |  |  | Transmital Date: 06-APR-2025
Document Title: Electrical Power & Control Drum Schedule & Cutting List |  |  |  |  | PEDCO Tr. No.: PEDCO-NISOC-0401-EL-TR-2979 |  |  | Transmital Date: 06-APR-2025
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-EL-LI-0003_D01 |  |  | CRS Status: | C4
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | This document shall be submitted after finalizing "Electrical Power & Control Cable Schedule" document. |  | BK-SUR-ENG-ELE-02-08934 | 2024-01-09 | اصلاحات انجام شده در مدرک Electrical Power & Control Cable Schedule مد نظر قرار گرفته و در مدرک Electrical Power & Control Drum Schedule & Cutting List اعمال گردید. |  |  | See Item 6 bellow
2 | This document shall be compatible with "Electrical Power & Control Cable Schedule", for example 3x2.5 and 10x2.5 type E has not been considered in this document, meanwhile there is not exist type L (Item 56), cable in cable schedule. It shall be rechecked and modified. |  | BK-SUR-ENG-ELE-02-08934 | 2024-01-09 | مدرک به صورت کلی مورد بازنگری قرار گرفته شد و اصلاحات لازم صورت پذیرفته است. |  |  | See Item 6 bellow
3 | All cables tag in "Cable No." column shall be specified based on cable schedule. The title "according to cable schedule" is not acceptable. |  | BK-SUR-ENG-ELE-02-08934 | 2024-01-09 | مدرک به صورت کلی مورد بازنگری قرار گرفته شد و اصلاحات لازم صورت پذیرفته است. |  |  | Noted, closed
4 | It shall be clarify what "Freeze" meean in description column. |  | BK-SUR-ENG-ELE-02-08934 | 2024-01-09 | در نسخه جدید عبارت freeze حذف گردید. |  |  | Noted, closed
5 | Complimentary comments will be submitted after submitting revised technical offer based on comments. |  | BK-SUR-ENG-ELE-02-08934 | 2024-01-09 | .NOTED |  |  | See Item 6 bellow
6 | با توجه به اينكه كامنتهاي متعدد مناطق و پتروايران بر روي مدرك cable schedule اعمال نشده اند و اين مدرك پيش نياز تهيه مدرك ‍Cutting است لذا ضروري است قبل از ارسال مدرك cutting، مدرك cable schedule به روز رساني و ارسال گردد. |  | BK-SUR-ENG-ELE-04-10182 | 2025-04-07 | مدرکcable schedule اصلاح شده و به همراه این مدرک ارسال میگردد.
7 | با توجه به كامنت مطرح شده در بند 6 مدارك ارسالي با ترنسميتالهاي 2978 و 2979 شامل مدارك زير براي مناطق نفت خيز ارسال نگرديد. MTO FOR POWER & CONTROL CABLES ELECTRICAL POWER & CONTROL DRUM SCHEDULE &CUTTING LIST |  | BK-SUR-ENG-ELE-04-10182 | 2025-04-07 | مدرک cable schedule اصلاح شده و به همراه این مدرک ارسال میگردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M.Karimi | Signature |  |  |  | Clarified By: | Signature
| Date: 07-APR-2025 |  |  |  |  | Date: