## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-PR-PI-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2057 |  |  | Transmital Date:05/01/2023
Document Title: P&ID - Condensate Pipeline (to Binak PU) |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0202-PR-TR-2057 |  |  | Transmital Date:05/01/2023
[5 empty] | CRS No: NISOC-CRS-BK-PPL-PEDCO-320-PR-PI-0002_D05 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | موارد مطروحه در نامه های شماره 447699 و 300274 این امور تا کنون بر روی این مدرک اعمال نگردیده است و پاسخ ارائه شده نیز مورد قبول این امور نمی باشد لذا ضروریست توصیه شماره 14 از مدرک HAZOP Report Pipeline اعمال گردد |  | 1402-2294-197101 | 1402/05/18 | کامنت شماره 13 مربوط به CHECK VALVE در نقشه شماره BK-W007S-PEDCO-110-PR-PI-0001 و همچنین کامنت شماره 14 مربوط به در نظر گرفتن ونت در نقشه شماره BK-W007S-PEDCO-110-PR-PI-0001 و کامنت مربوط به در نظر گرفتن درین کانکشن در نقشه شماره BK-GCS-PEDCO-120-PR-PI-0004 قبل از نقطه Tie Point اضافه خواهد شد، بنابراین این نقشه تغییری نخواهد داشت. جهت بررسی تغییرات به پیوست 1 و 2 رجوع گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021