## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-PR-PI-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2057 |  |  | Transmital Date: 01/05/2023
Document Title: P&ID - Condensate Pipeline (to Binak PU) |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0202-PR-TR-2057 |  |  | Transmital Date:01/05/2023
[5 empty] | CRS No: CRS-BK-PPL-PEDCO-320-PR-PI-0002_D05 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | HAZOP Recommendation شماره 13 و14 مربوط به بخش خط لوله، در مدرک P&ID منیفولد و در Tie-in شماره 8، اعمال گردد. |  | BK-SUR-ENG-PCS-02-07564 | 2023-05-18 | کامنت شماره 13 مربوط به CHECK VALVE در نقشه شماره BK-W007S-PEDCO-110-PR-PI-0001 و همچنین کامنت شماره 14 مربوط به در نظر گرفتن ونت در نقشه شماره BK-W007S-PEDCO-110-PR-PI-0001 و کامنت مربوط به در نظر گرفتن درین کانکشن در نقشه شماره BK-GCS-PEDCO-120-PR-PI-0004 قبل از نقطه Tie Point اضافه خواهد شد، بنابراین این نقشه تغییری نخواهد داشت. جهت بررسی تغییرات به پیوست 1 و 2 رجوع گردد.
2 | لازم است نقطه نظرات ذينفع اصلي اعمال گردد. |  | BK-SUR-ENG-PCS-02-07564 | 2023-05-01 | اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Maleki | Signature |  |  |  | Clarified By: | Signature
| Date: 08/05/2023 |  |  |  |  | Date: