## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-HV-MT-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2955 |  |  | Transmital Date: 19/FEB/2025
Document Title: MTO For HVAC & Plumbing For Extension of Existing Elect. Building |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0312-HV-TR-2955 |  |  | Transmital Date: 19/FEB/2025
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-HV-MT-0002_D02 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به مدرک محاسبات و دیتاشیت تجهیزات، ظرفیت کولرهای اسپلیت در ردیف 2 صفحه 4 از 5 اصلاح گردد. |  | 03/2294/516097 | 1403/12/22 | ظرفیت کولرهای اسپلیت در ردیف 2 صفحه 4 از 5 اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: 1403/12/22 |  |  |  |  | Date: