## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-MR-0007 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2839 |  |  | Transmital Date: 16 Nov 2024
Document Title: PMR For F&G Devices |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0308-IN-TR-2839 |  |  | Transmital Date: 16 Nov 2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-MR-0007_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اینکه پیمانکار جهت سرعت عمل در پروسه پروژه برای خرید کالای موضوع نامه اقدام به برگزاری مناقصه و تولید مدرک TBE نموده است، لازم است در مراحل خرید پیمانکار آخرین ویرایش تایید شده مدارک مرجع را در نظر بگیرید. نظر به تغییرات در آخرین ویرایش ارسال شده مدرک دیتاشیت مربوطه از مدارک مرجع نسبت به مدرک IFA تایید شده، مسولیت تاخیر زمانی در پروسه خرید کالا بر عهده پیمانکار می‌باشد. |  | 03/2294/368021 | 1403/09/13 | با توجه به نظر کارفرمای محترم، مدرک همراه با آخرین نسخه از مدارک ضمیمه بروزرسانی گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: