## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-PR-PI-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2490 |  |  | Transmital Date: 15/11/2023
Document Title: P&ID - Gas Pipeline (to Siahmakan G.I. Station) |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0208-PR-TR-2490 |  |  | Transmital Date: 15/11/2023
[5 empty] | CRS No: NISOC-CRS-BK-PPL-PEDCO-320-PR-PI-0001_D05 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | پاسخ پیمانکار مورد قبول نبوده است لذا عطف به نامه های شماره 43235، 300442 و همچنین نامه شماره 473531 می بایست دو عدد گیج فشار یکی برای رنج بالا و یکی برای رنج پایین بر روی تجهیز Pig launchet/Receiver نصب گردد. |  | 1402-2294-444454 | 1402/10/30 | عطف به نامه شماره 04/2294/8642 نیازی به در نظر گرفتن گیج فشاری نمی باشد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021