## CRS-Main
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-PR-PI-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2490 |  |  | Transmital Date: 15/11/2023
Document Title: P&ID-Gas Pipeline (to Siahmakan G.I. Station) |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0208-PR-TR-2490 |  |  | Transmital Date: 15/11/2023
[5 empty] | CRS No: CRS-BK-PPL-PEDCO-320-PR-PI-0001_D05 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به سایزهای مختلف 1 تا 8 اينچ فلنج های مورد استفاده از کلاس خط FN27، می بایست در مدارک Pipeline Material Specification و Calculation Note For Pipeline Wall Thickness برای کلاس خط FN27 کلیه سایزهای استفاده شده در نظر گرفته شود |  | BK-SUR-ENG-PCS-02-08834 | 2023-11-27 | اعمال می گردد.
2 | مطابق مدرك Symbol & Legend بايستي Finishing خط به UW اصلاح گردد |  | BK-SUR-ENG-PCS-02-08834 | 2023-11-27 | اعمال می گردد.
3 | میزان شیب تجهیز مشخص گردد. |  | BK-SUR-ENG-PCS-02-08834 | 2023-11-27 | مطابق با دیتاشیت تجهیز اضافه گردید.
4 | سایز نازل ورودی خط PSV، با توجه به معیار طراحی این خط که می بایست حداکثر 3% افت فشار Set pressure را داشته باشد مجددا بررسی گردد به نظر می رسد که سایز نازل مذکور می بایست به 2 اینچ اصلاح گردد. |  | BK-SUR-ENG-PCS-02-08834 | 2023-11-27 | مطابق توافق صورت گرفته با ذینفع اصلی سایز یک اینچ مورد تایید میباشد.
5 | لازم است نقطه نظرات ذينفع اصلي اعمال گردد. |  | BK-SUR-ENG-PCS-02-08834 | 2023-11-27 | اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Maleki | Signature |  |  |  | Clarified By: | Signature
| Date: 27/11/2023 |  |  |  |  | Date: