## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-ST-DW-0002 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-1991 |  |  | Transmital Date:4/5/2023
Document Title: Pipe Supports Structure Drawing For Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-ST-T-1991 |  |  | Transmital Date:4/5/2023
[5 empty] | CRS No:NISOC-CRS-BK-W007S-PEDCO-110-ST-DW-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | کامنت های دریافت شده روی فایل |  | BK-SUR-ENG-STR-02-07350 | 2023-04-08 | کلیه کامنت ها در فایل پیوست پاسخ داده شده است
Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Legend
| CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
Signature | Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: