## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK14-PEDCO-110-CV-PY-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1878 |  |  | Transmital Date: 15 FEB 2023
Document Title: Rough Grading Plans -BK14 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-T-1878 |  |  | Transmital Date: 15 FEB 2023
[5 empty] | CRS No: NISOC-CRS-BK-BK14-PEDCO-110-CV-PY-0003-D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 02/2294/6779 | 1402/01/09 | اعمال شد.
2 |  |  | 02/2294/6779 | 1402/01/09 | ابن فرآیند انجام شده است و مستندات آن در ضمائم تقدیم می گردد.
3 |  |  | 02/2294/6779 | 1402/01/09 | طبق شرح کار بایستی محوطه ای با مساحت 2050 مترمربع به محوطه بتنی اطراف سلر قدیمی اضافه شود. طبق نقشه برداری انجام شده، مساحت موجود محوطه بتنی حدود 640 مترمربع است که با کسر این عدد از مساحت نهایی محوطه بتنی یعنی 2560 مترمربع(64*40) به عدد 1920 مترمربع می رسیم. هم چنین جهت اجرای کامل محوطه بتنی نهایی با قطعه بندی استاندارد، نیازمند تخریب بخشی از بتن موجود به مساحت 130 مترمربع است. بنابراین میزان مشخص شده در شرح کار یعنی 2050 مترمربع (1920+130) شفاف می گردد. شکل روبرو توضیحات داده شده را نشان می دهد.
4 |  |  | 02/2294/6779 | 1402/01/09 | با توجه به میزان آب کم موردنیاز، تامین آب از طریق تانکر انجام می گردد.
5 |  |  | 02/2294/6779 | 1402/01/09
6 |  |  | 02/2294/6779 | 1402/01/09 | اعمال شد.
7 |  |  | 02/2294/6779 | 1402/01/09 | اعمال شد.
8 |  |  | 02/2294/6779 | 1402/01/09 | در 11 نقطه تعریض در نظر گرفته شده است و در نقشه های CV and Structure و هم چنین General Civil Layout که جزئیات جاده های دسترسی وجود دارد نشان داده شده است. محدوده این نقشه مختص لوکیشن است. به جدول شماره 4 برگه 92 نقشه Civil and Structure رجوع فرمایید.
9 |  |  | 02/2294/6779 | 1402/01/09 | اعمال شد.
10 |  |  | 02/2294/6779 | 1402/01/09 | اصلاح شد.
11 |  |  | 02/2294/6779 | 1402/01/09 | اصلاح شد.
12 |  |  | 02/2294/6779 | 1402/01/09 | مورد قبول است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: