## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-TB-0008-D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1933 |  |  | Transmital Date: 05/03/2023
Document Title: TBE For Chemical Injection Packages |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0112-ME-TR-1933 |  |  | Transmital Date: 05/03/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-TB-0008-D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Please find the attached comments. |  | BK-SUR-ENG-MEC-01-07251 | 2023-03-18 | Noted
2 | Green Mile Co : مطابق با مدرك Instrument Hookup Drawing سايز ‍Connection مربوط به LG,LT و LS مي بايست "2 - 300# در نظر گرفته شود. |  | BK-SUR-ENG-MEC-01-07251 | 2023-03-18 | به دلیل utility بودن پکیج Chemical طبق نظر I&C الزام به سایز "2 برای LT,LG,LS نمی باشد و "3/4 طبق کامنت داده شده برای وندور کافی است .
3 | در فايل TECHNICAL QUOTATION مي بايست مدارك زير اضافه گردد: Skid Drawing Welding Map Drawing Isometric Drawing Mixer Data Sheet Mixer Drawing Hookup Drawing MTO For Piping Component MTO For Tank Drawing |  | BK-SUR-ENG-MEC-01-07251 | 2023-03-18 | نقطه نظر کارفرمای محترم مد نظر قرار خواهد گرفت و همچنین مدارک درخواستی در مدرک VPIS نهایی خواهد شد.
4 | در مدارك ارسال شده DEVIATION LIST موجود نمي باشد. |  | BK-SUR-ENG-MEC-01-07251 | 2023-03-18 | در Technical proposal سازنده deviation list تحت عنوان clarification مطرح گردیده است.
5 | لازم به ذكر است كليه كامنت هاي ذينفع اصلي پروژه مي بايست در نظر گرفته شود و تاييد مدرك منوط به تاييد ذينفع اصلي پروژه مي باشد. |  | BK-SUR-ENG-MEC-01-07251 | 2023-03-18 | نقطه نظر کارفرمای محترم مد نظر قرار خواهد گرفت .
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature | H.Naserizadeh |  |  | Clarified By: H.Adineh | Signature
| Date: |  |  |  |  | Date: 01/MAY/2023