## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK15-PEDCO-110-EL-MR-0002_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1393 |  |  | Transmital Date: 11-Sep-2022
Document Title: PMR For LV Switchgear & MCC - BK15 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0106-EL-TR-1393 |  |  | Transmital Date: 11-Sep-2022
[5 empty] | CRS No: NISOC-CRS-BK-BK15-PEDCO-110-EL-MR-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در خصوص ساختار کلی مدرک نظر خاصی مطرح نمی باشد. لیکن از آنجا که برخی از مدارک با ویرایش های قید شده در بخش Reference هنوز نهایی نشده است، آخرین ویرایش مدارک تأیید شده (AFC) در مدرک درج گردد. |  | 1401-2294-249409 | 1401-07-13 | آخرین ویرایش مدارک پیوست به روزرسانی گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Gh.Sadaatian | Signature |  |  |  | Clarified By: | Signature
| Date: 24-Sep-22 |  |  |  |  | Date: