## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK12-PEDCO-110-EL-MR-0002_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1393 |  |  | Transmital Date: 11-Sep-2022
Document Title: PMR For LV Switchgear & MCC - BK12 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0106-EL-TR-1393 |  |  | Transmital Date: 11-Sep-2022
[5 empty] | CRS No: PEDCO-CRS-BK-BK12-PEDCO-110-EL-MR-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | "Spare Part List and Interchangeability Record" form shall be added to this document as attachement. |  | BK-SUR-ENG-ELE-01-05759 | 2022-09-24 | فرمت مدرک MR برای همه دیسیپلینها یکسان بوده و به تأیید کافرمای محترم رسیده است. لازم به ذکر است هنگام دریافت پیشنهادفنی از سازندگان مختلف، این فرمها دریافت خواهد شد.
2 | Following documents shall be added as reference documents in section 11.1, LIST OF REFERENCE / APPLICABLE DOCUMENTS: -Electrical design criteria -Specification For Painting -Document Numbering Procedure |  | BK-SUR-ENG-ELE-01-05759 | 2022-09-24 | مدارک مورد نیاز در لیست اضافه گردید.
3 | در بند 5.1.1، عبارت "QA Organization" به "QA/QC Organization Chart" تغيير يابد. |  | BK-SUR-ENG-ELE-01-05759 | 2022-09-24 | اعمال گردید.
4 | در جدول Attachment 2: - عبارت "List of Documents will be Finalized in VPIS" در نوتها اضافه گردد. |  | BK-SUR-ENG-ELE-01-05759 | 2022-09-24 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 24-Sep-22 |  |  |  |  | Date: