## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PI-DG-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1617 |  |  | Transmital Date: 11/27/2022
Document Title: Material flow Diagram |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1617 |  |  | Transmital Date: 11/27/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PI-DG-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | اظهار نظر در خصوص دیاگرام های انتخاب مواد پس از نهایی شدن مدرک مطالعات خوردگی و انتخاب مواد امکانپذیر می باشد. شایان ذکر است جهت تایید مدارک فوق الاشاره،نهایی سازی مدارک پیش نیاز در دستور کار تیم مهندسی آن پیمانکار قرار گیرد. |  | 1401-2294-393842 | 1401/10/17 | ویرایش D03 مدرک مطالعات خوردگی ایستگاه تقویت فشار بینک به آن کارفرمای محترم با ترنسمیتال T-1710 ارسال شده است. لازم به ذکر است با توجه به آخرین کامنت کارفرمای محترم بر روی مدرک مطالعات خوردگی، مدرک MFD متاثر نخواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021