## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PI-DG-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1617 |  |  | Transmital Date: 11/27/2022
Document Title: Material flow Diagram |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1617 |  |  | Transmital Date: 11/27/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PI-DG-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Material Flow Diagram shall be in accordance with final approved Piping corrosion study and Material Selection Report for GCS. |  | BK-SUR-ENG-PIP-01-06342 | 2022-12-04 | Corrosion study and Material Selection Report for GCS has been submitted. |  |  | See Item 6
2 | Material Flow Diagrams shall be in accordance with final P&ID's by identifying size and rating of all Valves, reducers and Equipment (if any). It is better to identify all Instruments, too. |  | BK-SUR-ENG-PIP-01-06342 | 2022-12-04 | This document revised based on last revision of PFD. |  |  | See Item 7
3 | The document Piping corrosion study and Material Selection Report BK-GCS-PEDCO-120-PI-RT-0001 shall be referred. All P&ID's of GCS shall be referred, too |  | BK-SUR-ENG-PIP-01-06342 | 2022-12-04 | Noted. |  |  | See Item 7 and 8
4 | Note 1 shall be added as follows: 1- WALL THICKNESS SHALL BE IN ACCORDANCE WITH WALL THICKNESS CALCULATION REPORT. |  | BK-SUR-ENG-PIP-01-06342 | 2022-12-04 | Noted. |  |  | Closed
5 | The material and Corrosion Allowance shall be specified for 4" Condensate Pipeline |  | BK-SUR-ENG-PIP-01-06342 | 2022-12-04 | According to calculations material should be C.S. + 6mm Corrosion allowance NACE. Relevant calculation will be presented in the next revision of Manifold corrosion study. This line exists and material selection is informative. |  |  | See Item 9
6 | تا زماني كه مدرك Piping corrosion study and Material Selection Report مربوط به GCS مورد تأييد قرار نگيرد نمي توان در خصوص اين مدرك اظهار نظر قطعي نمود. |  | BK-SUR-ENG-PIP-01-06342 | 2022-12-04 | ویرایش D03 مدرک مطالعات خوردگی ایستگاه تقویت فشار بینک به آن کارفرمای محترم با ترنسمیتال T-1710 ارسال شده است. لازم به ذکر است با توجه به کامنت کارفرمای محترم مبنی بر پیش نیازی MFD، مدرک پس از ارسال مدرک MFD به روزرسانی و متعاقبا به کارفرمای محترم ارسال خواهد شد
7 | در هر دياگرام بايستي PFD و P&ID مربوطه به عنوان مرجع در جدول ريفرنس ذكر گردد. |  | BK-SUR-ENG-PIP-01-06342 | 2022-12-04 | اعمال گردید.
8 | Material Flow Diagram بايستي براي تمامي بخش هاي GCS بر اساس PFD و P&ID مثل Fuel Gas و Closed Drain‌ و Firewater و Utility ها ارائه گردد. |  | BK-SUR-ENG-PIP-01-06342 | 2022-12-04 | در مدرک فوق صفحه Fuel Gas اضافه گردید. همچنین لازم به ذکر است مطابق رویه تمامی پروه های انجام شده توسط این پیمانکار و همچنین رویه معمول سایر پروژه های انجام شده در این حوزه ،Material Flow Diagram در ناحیه فرآیندی به صورت دیاگرام نمایش داده می شود و در سایر قسمت های پروژه از جمله UYILITY AREA فلسفه انتخاب متریال در مدرک Piping Corrosion Study & Material Selection Report ارائه می گردد.
9 | در دياگرام خط بصورت Existing 4" Condensate Pipeline معرفي گردد و توضيح پيمانكار در آيتم 5 فوق بصورت يك نوت در ديگرام اضافه گردد. |  | BK-SUR-ENG-PIP-01-06342 | 2022-12-04 | اعمال گردید. لازم به ذکر است با توجه به اینکه این خط موجود بوده و در حال حاضر در سرویس می باشد لذا مطالعات خوردگی در حیطه کاری این پیمانکار نمی باشد و نیازی به محاسبه حد مجاز خوردگی این خط نمی باشد.
10 | براي تمامي تجهيزات و لوله كشي داخل پكيج ها مثل Dehydrawtion Package بايستي متريال و CA در دياگرام مشخص گردند (بطور مثال براي Reboiler و خطوط آن مشخص گردد). |  | BK-SUR-ENG-PIP-01-06342 | 2022-12-04 | پس از دریافت اطلاعات از سازنده پکیج فوق ، اطلاعات مورد نظر ارائه خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021